ADOPTED – JANUARY 26, 2021

AGENDA ITEM NO. 28

Introduced by the Human Services and Finance Committees of the:

INGHAM COUNTY BOARD OF COMMISSIONERS

RESOLUTION TO AUTHORIZE NO-COST EXTENSION OF REINVESTMENT FUND GRANT AGREEMENT WITH INGHAM COUNTY HEALTH DEPARTMENT FOR INVEST HEALTH FIELD BUILDING INITIATIVE AND AMENDMENT TO RESOLUTION #20-572

RESOLUTION #21 – 032

WHEREAS, Ingham County Health Department (ICHD) wishes to extend the agreement with Reinvestment Fund through June 30, 2021 and to amend Resolution #20-752 to update the effective dates to February 1, 2021 through June 30, 2021 to reflect additional time needed to complete the fabrication and installation of a custom archway located between the properties of 3427 Pleasant Grove Road and 3505 Pleasant Grove Road in Lansing; and

WHEREAS, ICHD has previously accepted two funding awards totaling $105,000 from Reinvestment Fund to serve as the local fiduciary for the Lansing Invest Health Team as part of the national Invest Health Field Building (IHFB) program; and

WHEREAS, the first funding award was for $75,000 effective July 1, 2019 through September 30, 2020, and was authorized by the Ingham County Board of Commissioners (BOC) via Resolution #19-246; and

WHEREAS, the second funding award was for $30,000 effective February 1, 2020 through June 30, 2020, and was authorized by the Ingham County Board of Commissioners via Resolution #20-068; and

WHEREAS, on July 8, 2020, a short form extension request was approved by the Ingham BOC for a no-cost extension of these two funding awards through December 31, 2020; and

WHEREAS, as of July 1, 2020, $56,700 remained to be spent from the $105,000 in awarded funding and as of December 29, 2020, $11,796 remains to be spent from the $105,000 in awarded funding; and

WHEREAS, expenditure of the balance of funds as approved by Reinvestment Fund will be for the sole purpose of sub-contracting with Michigan Imagery for the period of February 1, 2021 through June 30, 2021 in the amount of $11,796 for fabrication and installation of a custom archway feature; and

WHEREAS, as the local fiduciary agent, ICHD supports the Lansing Invest Health Team’s pursuit of:

- Advancing policies and practices that position and align community investment systems to increase capital flows to racial equity-promoting built environment investments

- Taking steps to advance a pipeline of financeable built environment projects focused on increasing racial equity as part of a long-term community health improvement strategy; and

WHEREAS, the Health Officer recommends an extension of the existing Invest Health Field Building Grant Agreement with Reinvestment Fund through June 30, 2021, and authorizes entering into a sub-contract with Michigan Imagery for fabrication and installation of a custom metalwork entryway feature for the period February 1, 2021 through June 30, 2021.

THEREFORE BE IT RESOLVED that the Ingham County Board of Commissioners authorizes an extension to the existing IHFB Grant Agreement with Reinvestment Fund through June 30, 2021.

BE IT FURTHER RESOLVED, the Ingham County Board of Commissioners authorizes a sub-contract with Michigan Imagery in an amount not to exceed $11,796 for fabrication and installation of a custom metalwork entryway feature for the period February 1, 2021 through June 30, 2021.

BE IT FURTHER RESOLVED, that the Chairperson of the Board of Commissioners is hereby authorized to sign any necessary contract documents on behalf of the county after approval as to form by the County Attorney.

HUMAN SERVICES:  Yeas:  Tennis, Sebolt, Slaughter, Trubac, Graham, Naeyaert, Maiville

Nays:  None     Absent:  None     Approved  01/25/2021

FINANCE:  Yeas:  Grebner, Tennis, Crenshaw, Polsdofer, Stivers, Maiville

Nays:  None     Absent:  Schafer     Approved  01/20/2021