ADOPTED – JULY 28, 2026

AGENDA ITEM NO. 44

Introduced by the Law & Courts and Finance Committees of the:
INGHAM COUNTY BOARD OF COMMISSIONERS

RESOLUTION TO ADOPT THE 2027 JUVENILE JUSTICE COMMUNITY AGENCY PROCESS CALENDAR

RESOLUTION #26 – 376

WHEREAS, a Juvenile Justice Millage was approved by the voters of Ingham County in November of 2002, and subsequently renewed, for the purpose of funding an increase to Ingham County’s capacity to detain and house juveniles who are delinquent or disturbed, and to operate new and existing programs for the treatment of such juveniles; and  

WHEREAS, the Ingham County Board of Commissioners wishes to adopt a resolution to establish the 2026 Juvenile Justice Community Agency Process and to reserve Juvenile Justice Millage funds in the amount of $265,000 for this purpose; and

WHEREAS, of the $265,000 in Juvenile Justice Community Agency programs, a minimum of $150,000 shall be State of Michigan Child Care Fund reimbursement eligible at 75%. 

THEREFORE BE IT RESOLVED, that the Ingham County Board of Commissioners hereby adopts the attached 2027 Juvenile Justice Community Agency Process Calendar to establish timelines for the process.

LAW & COURTS:  Yeas:  Polsdofer, Willis, Peña, Cahill, Lawrence, Johnson

          Nays:  None     Absent:  Trubac, Schafer     Approved  07/16/26

FINANCE:  Yeas:  Grebner, Morgan, Tennis, Sebolt, Polsdofer, Pratt, Maiville

          Nays:  None    Absent:  None     Approved  07/22/26

2027 JUVENILE JUSTICE COMMUNITY AGENCY PROCESS CALENDAR
	July 28, 2026
	The Board of Commissioners adopts the 2026 Juvenile Justice Community Agency Process Calendar Resolution.

	July 29, 2026
	A press release is prepared announcing the availability of Juvenile Justice Community Agency funds and invites community organizations to submit an application. The application deadline is August 14, 2026 at 5:00 pm.

	August 14, 2026
	The Controller’s Office prepares a summary of the Juvenile Justice Community Agency applicants and forwards the summary to the County Attorney’s Office to ensure that the agency’s proposed purposes are legal under Michigan Law and comply with the intent of the Juvenile Justice Millage.

	September 22, 2026
	A Juvenile Justice Community Agency notebook is prepared by the Controller/Administrator’s Office. The notebook includes all agencies who submitted applications for review by the Law & Courts Committee.  (Notebook is distributed at the September 22, 2026 Board of Commissioners’ Meeting) 

	October 1, 2026


	The Law & Courts Committee reviews the Juvenile Justice Community Agency applications and makes recommendations for funding.  Juvenile Justice Community Agency applicants are invited to attend the Law & Courts Committee meeting.  The Law & Courts Committee makes their recommendations by resolution to the Finance Committee. 

	October 7, 2026
	The Finance Committee approves the resolution for Juvenile Justice Community Agency funding to the Board of Commissioners.

	October 13, 2026
	The Board of Commissioners authorizes a resolution for the 2027 Juvenile Justice Community Agency grant awards.

	October 16, 2026
	The Juvenile Justice Community Agency applications are sent to the County Attorney’s Office for contract preparation.

	October 16, 2026
	Juvenile Justice Community Agencies are notified of the County grant award and that a County contract will be forthcoming in December.

	December 2026
	Contracts are received from the County Attorney’s Office and mailed to the Juvenile Justice Community Agencies for appropriate signatures. When the contracts are mailed, a request is made to agencies to mail their Certificate of Insurances and a Revised Scope of Services if the grant award is different than the original requested amount.   

	January 2027
	Fifty percent of the grant award is sent to the Juvenile Justice Community Agency upon receipt of the agency’s signed contract and the appropriate documentation as listed above.

	July 2027
	The Juvenile Justice Community Agencies send their first six-month report to the Controller’s Office and upon review by staff, a check for the remaining portion of the grant is sent to the agency. 



